ENDOSCOPIC STOMACH SIMULATION — PROJECT SCHEDULE

3D Modeling Workflow  ·  Blender · 3D AI Studio · Unity  ·  Revised: May 2026

## Project Overview

The stomach shell is complete. This schedule covers generation of each internal anatomical part using 3D AI Studio, cleaned in Blender, then merged into the shell. Final export to Unity for real-time endoscopic simulation.

## Scope Changes (Revised Plan)

- Fundus (Retroflexed View) — removed from scope

- Incisura Angularis — removed from scope

- Hypopharynx — added as new Week 2 (after Z-Line)

- Duodenal Bulb (D1) — added as new Week 7 (endoscopic milestone: bulb lumen, anterior/posterior walls)

- Duodenal Interior / D1-D2 Junction — added as new Week 8 (endoscopic milestone: bulb interior folds, transition to descending duodenum)

## Current Progress (as of May 21, 2026)

- Week 1 — Z-Line & GEJ: COMPLETED

- Week 2 — Hypopharynx: COMPLETED

- Week 3 — Cardia Region: IN PROGRESS

## Week-by-Week Schedule

| Week | Dates | Anatomical Part | Weekly Target | Status |
| --- | --- | --- | --- | --- |
| Wk 1 | May 10 – May 14 | Z-Line & Gastroesophageal Junction (GEJ) | Collect reference images → generate mesh → merge with shell | DONE |
| Wk 2 | May 17 – May 21 | Hypopharynx | Collect reference images → generate mesh → merge with shell | DONE |
| Wk 3 | May 24 – May 28 | Cardia Region | Collect reference images → generate mesh → merge with shell | IN PROGRESS |
| Wk 4 | May 31 – Jun 04 | Gastric Body & Rugae Folds | Collect reference images → generate mesh (3 days) → merge with shell | UPCOMING |
| Wk 5 | Jun 7 – Jun 11 | Pyloric Antrum | Collect reference images → generate mesh → merge with shell | UPCOMING |
| Wk 6 | Jun 14 – Jun 18 | Pylorus & Pyloric Sphincter | Collect reference images → generate mesh → merge with shell | UPCOMING |
| Wk 7 | Jun 21 – Jun 25 | Duodenal Bulb (D1) | Collect EGD reference images of bulb lumen, anterior/posterior walls → generate mesh → merge | UPCOMING |
| Wk 8 | Jun 28 – July 2 | Duodenal Interior / D1-D2 Junction | Collect EGD images of bulb interior folds, D1-D2 transition → generate mesh → merge | UPCOMING |
| Wk 9 | July 5 – Jul 9 | Full Integration, Polish & Validation | Seam audit → materials/render → validation → final Unity export | UPCOMING |

Naming convention: PART_W[n]_[RegionName]  ·  Merge rule: Validate each merge before proceeding to next week  ·  Total: 9 weeks · Completion target: July 9, 2026